## C-Dashboard
UK Cutover Plan |  | DASBOARD VALUES
IRE Plan Sheet Name | C-Detailed Plan | Completion Status | Cutover | Rollback |  | Total Tasks | UK Cutover Exec | UK Rbk Exec | Cutover Tasks in Past | RbkTasks in Past
Start Line Number | 5 | Completed | 57.62% | 0% | Cutover | 21 | 8 | 0 | 4 | 0
End Line Number | 1000 | Remaining | 42.38% | 100% | Rollback | 21
Task Name Col | A
Dry Run Date Col | B | Dashboard Date : |  |  |  |  | 2020-08-23
Dry Run Exec Status Col | H | Cutover |  | Go Live |  | 2020-01-15 | Rollback
UK Rollback Plan |  | Green | Comment: |  |  |  | Green | Comment:
UK Plan Sheet Name | C-Rollback Plan
Start Line Number | 5
End Line Number | 1000
Task Name Col | A
Date Col | B
Exec Status Col | H
|  | 8 tasks executed to date out of 21 total tasks |  |  |  |  | 0 tasks executed to date out of 21 total tasks
|  | 4 task(s) behind schedule | Reason and resolution plan: |  |  |  | 0 task(s) behind schedule | Reason and resolution plan:

## C-HL View
 | time axis 2019-12-23 to 2020-07-20
Status Icon | 2020-01-16: GO LIVE
High Level Activity 4
High Level Activity 1
[17 empty] | High Level Activity 2 |  |  |  |  | High Level Activity 5
Activity 3

## C-Detailed Plan
Go Live Date | 2020-01-15
Prod Sr No | y to | Day To Go Live | Est Time | Duration (Min) | Actual Time | Actual duration | Exec Status | System Id | Cutover Activities | Team owner | Task owner | Task Status | Comments | 0
[9 empty] | START: SECTION 1 NAME |  |  |  |  | 0
Sub Section 1 Name
cuttaskid5 | 2020-01-10 | -5 | 9:00 | 60 | 9:00 | 45 | 100% | System 1 | Task 1 Description | Team 1 | Name 1 | Confirmed
cuttaskid6 | 2020-01-10 | -5 | 10:00 | 10 | 9:45 | 5 | 100% | Comms | Comms 1: Message | Team 2 | Name 5 | Confirmed
cuttaskid7 | 2020-01-10 | -5 | 10:10 | 30 | 9:50 | 35 | 80% | System 1 | Task 2 Description | Team 1 | Name 2 | Confirmed
cuttaskid8 | 2020-01-11 | -4 | 10:40 | 10 | 10:25 | 0 | 0% | System 3 | Task 3 Description | Team 3 | Name 13 | Cancelled
cuttaskid9 | 2020-01-11 | -4 | 10:50 | 30 | 10:25 | 28 | 10% | System 2 | Task 4 Description | Team 2 | Name 7 | To Be Reviewed
Sub Section 2 Name
cuttaskid11 | 2020-01-11 | -4 | 9:00 | 60 | 9:00 | 45 | 100% | System 1 | Task 5 Description | Team 1 | Name 1 | Confirmed
cuttaskid12 | 2020-01-12 | -3 | 10:00 | 10 | 9:45 | 5 | 100% | Comms | Comms 2: Message | Team 2 | Name 5 | Confirmed
cuttaskid13 | 2020-01-12 | -3 | 10:10 | 30 | 9:50 | 35 | 80% | System 1 | Task 6 Description | Team 1 | Name 2 | Confirmed
cuttaskid14 | 2020-01-12 | -3 | 10:40 | 10 | 10:25 | 0 | 0% | System 3 | Task 3 Description | Team 3 | Name 13 | Cancelled
cuttaskid15 | 2020-01-12 | -3 | 10:50 | 30 | 10:25 | 28 | 10% | System 2 | Task 7 Description | Team 2 | Name 7 | To Be Reviewed
[9 empty] | END: SECTION 1 NAME |  |  |  |  | 0
[9 empty] | START: SECTION 2 NAME |  |  |  |  | 0
Sub Section 1 Name
cuttaskid19 | 2020-01-13 | -2 | 9:00 | 60 | 9:00 | 45 | 100% | System 1 | Task 8 Description | Team 1 | Name 1 | Confirmed
cuttaskid20 | 2020-01-13 | -2 | 10:00 | 10 | 9:45 | 5 | 100% | Comms | Comms 3: Message | Team 2 | Name 5 | Confirmed
cuttaskid21 | 2020-01-13 | -2 | 10:10 | 30 | 9:50 | 35 | 80% | System 1 | Task 9 Description | Team 1 | Name 2 | Confirmed
cuttaskid22 | 2020-01-13 | -2 | 10:40 | 10 | 10:25 | 0 | 0% | System 3 | Task 10 Description | Team 3 | Name 13 | Cancelled
cuttaskid23 | 2020-01-13 | -2 | 10:50 | 30 | 10:25 | 28 | 10% | System 2 | Task 11 Description | Team 2 | Name 7 | To Be Reviewed
Sub Section 2 Name
cuttaskid25 | 2020-01-14 | -1 | 9:00 | 60 | 9:00 | 45 | 100% | System 1 | Task 12 Description | Team 1 | Name 1 | Confirmed
cuttaskid26 | 2020-01-14 | -1 | 10:00 | 10 | 9:45 | 5 | 100% | Comms | Comms 4: Message | Team 2 | Name 5 | Confirmed
cuttaskid27 | 2020-01-14 | -1 | 10:10 | 30 | 9:50 | 35 | 80% | System 1 | Task 13 Description | Team 1 | Name 2 | Confirmed
cuttaskid28 | 2020-01-14 | -1 | 10:40 | 10 | 10:25 | 0 | 50% | System 3 | Task 14 Description | Team 3 | Name 13 | Cancelled
cuttaskid29 | 2020-01-14 | -1 | 10:50 | 30 | 10:25 | 28 | 10% | System 2 | Task 15 Description | Team 2 | Name 7 | To Be Reviewed
[9 empty] | END: SECTION 2 NAME |  |  |  |  | 0
[9 empty] | GO LIVE | [5 empty] | 0
cuttaskid32 | 2020-01-15 | 0 | 0:00 | 10 | 0:00 | 5 | 0% | Comms | Comms Final: Go Live | Team 2 | Name 5 | Confirmed

## C-Rollback Plan
Go Live Date | 2020-01-15
Prod Sr No | Start Date | Day To Go Live | Est Time | Duration (Min) | Real Time | Real duration | Exec Status | System Id | Rollback Activities | Team owner | Task owner | Task Status | Comments | 0
[9 empty] | START: SECTION 1 NAME |  |  |  |  | 0
Sub Section 1 Name
cuttaskid5 | 2020-01-10 | -5 | 9:00 | 60 | 9:00 | 45 | 0% | System 1 | Task 1 Description | Team 1 | Name 1 | Confirmed
cuttaskid6 | 2020-01-10 | -5 | 10:00 | 10 | 9:45 | 5 | 0% | Comms | Comms 1: Message | Team 2 | Name 5 | Confirmed
cuttaskid7 | 2020-01-10 | -5 | 10:10 | 30 | 9:50 | 35 | 0% | System 1 | Task 2 Description | Team 1 | Name 2 | Confirmed
cuttaskid8 | 2020-01-11 | -4 | 10:40 | 10 | 10:25 | 0 | 0% | System 3 | Task 3 Description | Team 3 | Name 13 | Cancelled
cuttaskid9 | 2020-01-11 | -4 | 10:50 | 30 | 10:25 | 28 | 0% | System 2 | Task 4 Description | Team 2 | Name 7 | To Be Reviewed
Sub Section 2 Name
cuttaskid11 | 2020-01-11 | -4 | 9:00 | 60 | 9:00 | 45 | 0% | System 1 | Task 5 Description | Team 1 | Name 1 | Confirmed
cuttaskid12 | 2020-01-12 | -3 | 10:00 | 10 | 9:45 | 5 | 0% | Comms | Comms 2: Message | Team 2 | Name 5 | Confirmed
cuttaskid13 | 2020-01-12 | -3 | 10:10 | 30 | 9:50 | 35 | 0% | System 1 | Task 6 Description | Team 1 | Name 2 | Confirmed
cuttaskid14 | 2020-01-12 | -3 | 10:40 | 10 | 10:25 | 0 | 0% | System 3 | Task 3 Description | Team 3 | Name 13 | Cancelled
cuttaskid15 | 2020-01-12 | -3 | 10:50 | 30 | 10:25 | 28 | 0% | System 2 | Task 7 Description | Team 2 | Name 7 | To Be Reviewed
[9 empty] | END: SECTION 1 NAME |  |  |  |  | 0
[9 empty] | START: SECTION 2 NAME |  |  |  |  | 0
Sub Section 1 Name
cuttaskid19 | 2020-01-13 | -2 | 9:00 | 60 | 9:00 | 45 | 0% | System 1 | Task 8 Description | Team 1 | Name 1 | Confirmed
cuttaskid20 | 2020-01-13 | -2 | 10:00 | 10 | 9:45 | 5 | 0% | Comms | Comms 3: Message | Team 2 | Name 5 | Confirmed
cuttaskid21 | 2020-01-13 | -2 | 10:10 | 30 | 9:50 | 35 | 0% | System 1 | Task 9 Description | Team 1 | Name 2 | Confirmed
cuttaskid22 | 2020-01-13 | -2 | 10:40 | 10 | 10:25 | 0 | 0% | System 3 | Task 10 Description | Team 3 | Name 13 | Cancelled
cuttaskid23 | 2020-01-13 | -2 | 10:50 | 30 | 10:25 | 28 | 0% | System 2 | Task 11 Description | Team 2 | Name 7 | To Be Reviewed
Sub Section 2 Name
cuttaskid25 | 2020-01-14 | -1 | 9:00 | 60 | 9:00 | 45 | 0% | System 1 | Task 12 Description | Team 1 | Name 1 | Confirmed
cuttaskid26 | 2020-01-14 | -1 | 10:00 | 10 | 9:45 | 5 | 0% | Comms | Comms 4: Message | Team 2 | Name 5 | Confirmed
cuttaskid27 | 2020-01-14 | -1 | 10:10 | 30 | 9:50 | 35 | 0% | System 1 | Task 13 Description | Team 1 | Name 2 | Confirmed
cuttaskid28 | 2020-01-14 | -1 | 10:40 | 10 | 10:25 | 0 | 0% | System 3 | Task 14 Description | Team 3 | Name 13 | Cancelled
cuttaskid29 | 2020-01-14 | -1 | 10:50 | 30 | 10:25 | 28 | 0% | System 2 | Task 15 Description | Team 2 | Name 7 | To Be Reviewed
[9 empty] | END: SECTION 2 NAME |  |  |  |  | 0
[9 empty] | Rollback Completed | [5 empty] | 0
cuttaskid32 | 2020-01-15 | 0 | 0:00 | 10 | 0:00 | 5 | 0% | Comms | Comms Final: Rollback Completed | Team 2 | Name 5 | Confirmed

## Actions Log
Date | Area | Notes/Action | Owner | Status | Update Date | Comments
2020-01-01 | Area1 | Action 1 | Owner 1 | Completed | 2020-01-02
2020-01-02 | Area2 | Action 2 | Onwer 2 | In progress
2020-01-03 | Area3 | Action 3 | Owner 2 | Open

## Contacts
Team | Name | Role | Comms Group | Intro Priority | Intro Meeting | Workshop | Workshop Date | Email | Phone number | Count | Team Unique List
Team 1 | Name 1 | Role 1 | Group 1 | [6 empty] | 4 | Team 1 | Name 1 | Name 2 | Name 3 | Name 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Team 1 | Name 2 | Role 2 | Group 1 | NA | NA |  |  |  |  | 6 | Team 2 | Name 5 | Name 6 | Name 7 | Name 8 | Name 9 | Name 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Team 1 | Name 3 | Role 3 | Group 1 | [6 empty] | 7 | Team 3 | Name 11 | Name 12 | Name 13 | Name 14 | Name 15 | Name 16 | Name 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Team 1 | Name 4 | Role 4 | Group 1 | NA | NA |  |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Team 2 | Name 5 | Role 5 | Group 1 | 1 | 2020-05-01 | 1 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Team 2 | Name 6 | Role 6 | Group 1 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Team 2 | Name 7 | Role 7 | Group 1 | 1 | 2020-05-01 | 1 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Team 2 | Name 8 | Role 8 | Group 1 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Team 2 | Name 9 | Role 9 | Group 2 | 1 | 2020-05-04 | 1 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Team 2 | Name 10 | Role 10 | Group 2 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Team 3 | Name 11 | Role 11 | Group 2 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Team 3 | Name 12 | Role 12 | Group 2 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Team 3 | Name 13 | Role 13 | Group 2 | 2 |  | 1 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Team 3 | Name 14 | Role 14 | Group 2 | 1 | 2020-04-28 | 1 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Team 3 | Name 15 | Role 15 | Group 2 | 2 |  | 1 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Team 3 | Name 16 | Role 16 | Group 3 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Team 3 | Name 17 | Role 17 | Group 3 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0